## Sheet1
S.No. | Workspace | Category | Defects
1 | Automation Overview | Defect | Change all buttons to coral colour as per the attachment
2 | Automation Overview | Defect | Change all font color where it is currently showing as red to coral colour
3 | Automation Overview | Defect | Page scrolls beyond the page limit in Automation Overview page
4 | Automation Overview | Defect | Good Morning badge should be based on the time of the day
5 | Automation Overview | Defect | Pick up where you left: Clicking open in compose just navigates to compose tab but not actually opening the test case which was actually selected
6 | Automation Overview | Defect | Recent Execution: Once again simply navigates to Audit and Evidence, doesn't open the actual evidence selected
7 | Automation Overview | Defect | Global Search Syntax error
8 | Automation Overview | Defect | Needs Attention Section > Clicking open audit and evidence is not filtering just the failed test cases
9 | Automation Overview | Documentation | Retry message "Some workspace data is unavailable. You can retry without leaving this page." What is not available?
10 | Automation Overview | Defect | Help: Create each topic as a collapsable sections
11 | All Workspaces | Defect | Use consistent theme in button shapes, some are pills and some of rounded rectangle. Stick to pill across the board
12 | Control Object Repository | Defect | Not sure if this is a quirk - when I capture the logon screen, no controls are identified, see attached
13 | Control Object Repository | New Feature | Compose : Make the fields sortable, see attached
14 | Control Object Repository | Documentation | Target: Non-production · verification required before execution > Add a note with a quick explanation
15 | Control Object Repository | Documentation | No stable id — this control's identifier regenerates on every reload, so saving it would break on the next run. If you're trying to capture a value shown after an action (e.g. a generated document/order number), use "Capture Document Number from Success Dialog" in Compose instead — it reads the confirmation message directly, no capture needed Needs explanation
16 | Control Object Repository | Documentation | What are the text boxes in capture screen
17 | Control Object Repository | Defect | Mass Capture results do not have an option to select the required controls to save them
18 | Compose | Documentation | Explain legacy test contract > Include details under help
19 | Compose | Documentation | Explain Use Inferred Contract> Include details under help
20 | Compose | Documentation | What does publish test do > Include details under help
21 | Compose | Defect | Open Text > Domain > shows values under the field; It would be ideal to show the values under a drop down showing the current selected value. Provide option add new This has to be consistently fixed across the workspaces
22 | Compose | Defect | Looks like domain and test process area are used interchangeably, follow a consistent language
23 | Test Data | Defect | Search is not working
24 | Test Data | Defect | The row data is very cluttered and the values are not clearly visible
25 | Test Data | Documentation | Explain how the column schema works
26 | Test Data | Documentation | A complete guide is required on how to use relational csv builder
27 | Test Data | Documentation | A complete guide is required on Stage topology and typed hand-offs
28 | Execution Center | Documentation | A complete how to guide is required for all execution types
29 | Audit and Evidence | Defect | Why is test case id showing as blank?
30 | Audit and Evidence | Defect | Duration is showing empty
31 | Audit and Evidence | Defect | Passed, View Record, Evidence PDF are not aligned
32 | Audit and Evidence | Defect | Search field is not fully visible. Not sure what the second field does
33 | Audit and Evidence | Defect | Need a better way of organizing / grouping the evidence documents. As the volumes increase, user has to keep scrolling